## ProjectTeam
Name | GitHub Alias
Kevin Tippenhauer | k-tipp
Aline Zaugg | zauga5
Lukas Wyss | wyslu1
Martin Stierlin | streuli13
Alain Roth | rotha6
Philipp Schaad | schap18

## Product Backlog
ID | Story Name | Description | Remarks | Priority | Effort Plan Original [h] | Effort Plan Updated [h] | Effort Actual [h] | Status
1 | User authentication | a user authenticates himself with a nfc card and a password | NFC authentication is not part of the realisation. | medium | 0 | 0 | 0 | waiting
2 | View assigned patients | load the assigned patients for a specific user. Present the patients with a status symbole. The status symbol shows if the patient needs the attention of a doctor/therapist. |  | high | 17 | 0 | 0 | waiting
3 | Show a single patient | show a single patient with a picture to the user. The needed informations are: Gender, Name, Address, Phone number, Emergency contact (Name, Address, Phone number), General Informations to the user, the security level of the patient |  | high | 17 | 0 | 0 | waiting
4 | Initiate new appointment | The user can initiate a new appointment with a patient. He should be able to select a date and how accurate the appointment has to be to the date. The MTA makes the final appointment in this range with the patient. |  | low | 6 | 0 | 0 | waiting
5 | Prescribe a new medication | A doctor should be able to prescribe a new medication. Informations: Medication, times per day, times in week, overall time, dose, measuring unit for the dose. |  | high | 20 | 0 | 0 | waiting
6 | Security tests on medication prescription | Every medication prescription has to be checked on interactions, kontra indications, and the selected dose. The doctor should be able to force a prescription in any case. | Not part of the realisation. | high | 0 | 0 | 0 | waiting
7 | Show the compendium informations | For every medication is the medication compendium available. |  | medium | 11 | 0 | 0 | waiting
8 | Show the current medication | All users (therapists and doctors) can view the current medication of a patient. |  | high | 8.5 | 0 | 0 | waiting
9 | Change the current medication | A doctor can change the current medication of a patient |  | medium | 3 | 0 | 0 | waiting
10 | Delete the current medication | A doctor can remove a prescribed medication of a patient. |  | high | 3 | 0 | 0 | waiting
11 | Prescribe a new therapy | A therapist can prescribe new therapies. The needed informations for a prescription are: Therapy name, times daily, on days in week, total duration of the therapy |  | high | 23 | 0 | 0 | waiting
12 | Show therapy plan | Show the prescribed therapies to the user |  | high | 8 | 0 | 0 | waiting
13 | Change therapy plan | A therapist can change a prescribed therapy of a patient |  | medium | 8 | 0 | 0 | waiting
14 | Delete therapy plan | A therapist can delete a prescribed therapy of a patient |  | high | 8 | 0 | 0 | waiting
15 | Display SOAP list | A SOAP list should be available for every patient. |  | low | 5 | 0 | 0 | waiting
16 | Create new SOAP entry | Therapists and docters can create new soap entries. |  | low | 5 | 0 | 0 | waiting
17 | Delete a SOAP entry | Therapists and docters can delete SOAP entries. |  | low | 5 | 0 | 0 | waiting
18 | Add test data | add test data |  | high | 5
19 | Cleanup Sprint 1 | cleanup code |  | high | 15
20
21 | State pattern implementation | Add a stop watch |  | high | 2
[5 empty] | 169.5 | 0 | 0

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Lukas | Martin | Kevin | Philipp | Aline | Alain | Effort Actual | Status
1.1 | 3 | Database | Create tables | Database
1.2 | 3 | User Model | Create JPA Model and Repository | Model/Repo
1.3 | 3 | Create authentication view | Create View | View
1.4 | 3 | Authentication controller | Add functionality | UI, Controller | [13 empty] | Keine Testklassen
2.1 | 1 | Database | Create tables | Database | Martin, Lukas | Kevin |  | 4 |  | 2 | 2 |  |  |  |  | 4 | Running | Medication interaktion/validation
2.2 | 1 | Patient Model | Create JPA Model and Repository | Model/Repo | Martin, Lukas | Kevin |  | 2 |  | 1 | 1 |  |  |  |  | 2 | Running | (Images speichern)
2.3 | 1 | Create overview view | Create View | View | Kevin, Martin | Lukas |  | 4 |  |  | 2 | 2 |  |  |  | 4 | Running
2.4 | 1 | Patient overview controller | Add functionality | UI, Controller | Kevin, Martin, Lukas | Kevin |  | 4 |  | 3 | 2 | 3 |  |  |  | 8 | Running
2.5 | 1 | Planning&Research | Planing and research | All | Kevin | All |  | 3 |  |  |  | 5 |  |  |  | 5 | Running
3.1 | 1 | Database | Create tables | Database | Martin, Lukas | Kevin |  | 3 |  | 2 | 1 | 1 |  |  |  | 4 | Running
3.2 | 1 | Patient Model | Create JPA Model and Repository | Model/Repo | Martin, Lukas | Kevin |  | 3 |  | 2 | 2 | 1 |  |  |  | 5 | Running
3.3 | 1 | Create single patient view | Create View | View | Kevin, Aline | Martin |  | 4 |  |  | 1 | 1 |  | 2 |  | 4 | Running
3.4 | 1 | Single patient view controller | Add functionality | UI, Controller | Kevin, Martin, Lukas | Lukas |  | 4 |  | 2 | 1 | 2 |  |  |  | 5 | Running
3.5 | 1 | Planning&Research | Planing and research | All | Kevin | All |  | 3 |  |  |  | 2 |  |  |  | 2 | Running
4.1 | 2 | Database | Create tables | Database | Martin, Lukas | kevin |  | 2 |  | 1 | 1 |  |  |  |  | 2
4.2 | 2 | Appointment Model | Create JPA Model and Repository | Model/Repo | Philipp | Alain |  | 2 | [7 empty] | 0
4.3 | 2 | Appointment controller | Add functionality | UI, Controller | Alain | Philipp |  | 2 | [7 empty] | 0
4.4 | 2 | Planning&Research | Planing and research | All | Kevin | All |  | 0.5 |  |  |  | 0.25
5.1 | 2 | Database | Create tables | Database | Martin, Lukas | Aline |  | 2 |  |  |  | 0.5 |  |  |  | 0.5
5.2 | 2 | Medication Model | Create JPA Model and Repository | Model/Repo | Alain | Aline |  | 2 |  |  |  | 0.5 |  |  |  | 0.5
5.3 | 2 | Create medication prescription view | Create View | View | Kevin | Philipp |  | 2 |  |  |  | 2 |  |  |  | 2
5.4 | 2 | Medication Controller | Add functionality | UI, Controller | Aline, Philipp | Kevin |  | 14 |  |  |  | 3 |  | 3 |  | 6
5.5 | 2 | Planning&Research | Planing and research | All | Kevin | All |  | 0.5 |  |  |  | 0.25
6.1 | 9999 | Database | Create tables | Database | Martin, Lukas | Alain | [9 empty] | 0
6.2 | 9999 | Medication Model | Create JPA Model and Repository | Model/Repo | Philipp | Alain | [9 empty] | 0
6.3 | 9999 | Create medication validation view | Create View | View | Martin, Lukas | Kevin | [9 empty] | 0
6.4 | 9999 | Medication validation controller | Add functionality | UI, Controller | Martin, Lukas | Kevin | [9 empty] | 0
6.5 | 9999 | Planning&Research | Planing and research | All | Kevin | All
7.1 | 2 | Database | Create tables | Database | Alain | Martin, Lukas |  | 1 | [7 empty] | 0
7.2 | 2 | Medication Model | Create JPA Model and Repository | Model/Repo | Philipp | Aline |  | 3 | [7 empty] | 0
7.3 | 2 | Create compendium view | Create View | View | Aline | Philipp |  | 2 | [5 empty] | 1.5 |  | 1.5
7.4 | 2 | Compendium controller | Add functionality | UI, Controller | Alain | Philipp |  | 5 |  |  |  | 0.5 |  |  |  | 0.5
7.5 | 2 | Planning&Research | Planing and research | All | Kevin | All |  | 0.5 |  |  |  | 0.25
8.1 | 2 | Create current Medication view | Create View | View | Aline | Philipp |  | 2 |  | 0.5 | 0.5 | 0.5 |  | 1 |  | 2.5
8.2 | 2 | Current medication controller | Add functionality | UI, Controller | Philipp | Alain |  | 5 |  | 1 | 1 | 0.5 |  |  |  | 2.5
8.3 | 2 | Planning&Research | Planing and research | All | Kevin | All |  | 0.5 |  |  |  | 0.25
9.1 | 2 | Add change button to current medication view | Create View | View | Aline | Kevin |  | 1 |  | 0.1 | 0.1 |  |  |  |  | 0.2
9.2 | 2 | medication change controller | Add functionality | UI, Controller | Aline | Alain |  | 2 | [7 empty] | 0
9.3 | 2 | Planning&Research | Planing and research | All | Kevin | All |  | 0.5 |  |  |  | 0.25
10.1 | 2 | Add delete button to current medication view | Create View | View | Aline | Kevin |  | 1 | [5 empty] | 1 |  | 1
10.2 | 2 | medication delete controller | Add functionality | UI, Controller | Philipp | Aline |  | 2 | [7 empty] | 0
10.3 | 2 | Planning&Research | Planing and research | All | Kevin | All |  | 0.5 |  |  |  | 0.25
18.1 | 2 | Create test data | create test data | Database | Alain | All |  | 5 | [6 empty] | 1 | 1
19.1 | 2 | Cleanup sprint 1 | cleanup and documentation | All | Kevin, Martin, Lukas | All |  | 15 |  | 1 | 1 | 3 |  |  |  | 5
20.1 | 2 | State pattern implementation | Add a stop watch | View, Controller | Kevin | Martin |  | 1 | [7 empty] | 0
0
0
0
0
0
0
0
0
|  | Totale Arbeitszeiten | [5 empty] | 108 |  | 15.6 | 15.6 | 29 | 0 | 8.5 | 1 | 68.2

## Tabelle1
| Kevin | Martin | Lukas
2015-11-28 | 5 | 2 | 2
| Demo Vaadin | Model | Model
2015-12-02 | 9 | 9 | 9
2015-12-03 | 2 | 2 | 2
| 14 | 11 | 11

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180