## ProjectTeam
Name | GitHub Alias
Kevin Tippenhauer | k-tipp
Aline Zaugg | zauga5
Lukas Wyss | wyslu1
Martin Stierlin | streuli13
Alain Roth | rotha6
Philipp Schaad | schap18

## Product Backlog
ID | Story Name | Description | Remarks | Priority | Effort Plan Original [h] | Effort Plan Updated [h] | Effort Actual [h] | Status
1 | User authentication | a user authenticates himself with a nfc card and a password | NFC authentication is not part of the realisation. | medium |  | 0 | 0 | waiting
2 | View assigned patients | load the assigned patients for a specific user. Present the patients with a status symbole. The status symbol shows if the patient needs the attention of a doctor/therapist. | GUI: Philipp | high |  | 0 | 0 | waiting
3 | Show a single patient | show a single patient with a picture to the user. The needed informations are: Gender, Name, Address, Phone number, Emergency contact (Name, Address, Phone number), General Informations to the user, the security level of the patient | GUI: Philipp | high |  | 0 | 0 | waiting
4 | Initiate new appointment | The user can initiate a new appointment with a patient. He should be able to select a date and how accurate the appointment has to be to the date. The MTA makes the final appointment in this range with the patient. | GUI: Philipp | low |  | 0 | 0 | waiting
5 | Prescribe a new medication | A doctor should be able to prescribe a new medication. Informations: Medication, times per day, times in week, overall time, dose, measuring unit for the dose. | GUI: Philipp | high |  | 0 | 0 | waiting
6 | Security tests on medication prescription | Every medication prescription has to be checked on interactions, kontra indications, and the selected dose. The doctor should be able to force a prescription in any case. | GUI: Philipp | high |  | 0 | 0 | waiting
7 | Show the compendium informations | For every medication is the medication compendium available. | GUI: Aline | medium |  | 0 | 0 | waiting
8 | Show the current medication | All users (therapists and doctors) can view the current medication of a patient. | GUI: Philipp | high |  | 0 | 0 | waiting
9 | Change the current medication | A doctor can change the current medication of a patient | GUI: Philipp | medium |  | 0 | 0 | waiting
10 | Delete the current medication | A doctor can remove a prescribed medication of a patient. | GUI: Philipp | high |  | 0 | 0 | waiting
11 | Prescribe a new therapy | A therapist can prescribe new therapies. The needed informations for a prescription are: Therapy name, times daily, on days in week, total duration of the therapy | GUI: Aline | high |  | 0 | 0 | waiting
12 | Show therapy plan | Show the prescribed therapies to the user | GUI: Aline | high |  | 0 | 0 | waiting
13 | Change therapy plan | A therapist can change a prescribed therapy of a patient | GUI: Aline | medium |  | 0 | 0 | waiting
14 | Delete therapy plan | A therapist can delete a prescribed therapy of a patient | GUI: Aline | high |  | 0 | 0 | waiting
15 | Display SOAP list | A SOAP list should be available for every patient. | GUI: Aline | low |  | 0 | 0 | waiting
16 | Create new SOAP entry | Therapists and docters can create new soap entries. | GUI: Aline | low |  | 0 | 0 | waiting
[5 empty] | 0 | 0 | 0

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 3
1.2 | 3 | User Model | Data model for user needs to be created based on authentication properties | Model |  | Kevin |  |  |  |  | waiting
1.3 | 3 | Authentication service | Test service for authentication (WSDL, demo endpoint) | Server side | Kevin | Kevin |  |  |  |  | waiting
1.4 | 3 | Login UI | Login UI with username and password | UI, Controller |  | Kevin |  |  |  |  | waiting
1.5 | 3 | Authentication Test | Create Testcases | Test |  | Kevin |  |  |  |  | waiting
2.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5
2.2 | 1 | Patient Model | Data model for patient needs to be created/adapted. | Model | Martin | Kevin |  |  |  |  | waiting
2.4 | 1 | Patient List View | Create view | UI | Philipp | Kevin |  |  |  |  | waiting
2.5 | 1 | Patient Controller | Functionality for patient list | Controller | Alain | Kevin
2.5 | 1 | Patient List Test | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
3.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
3.2 | 1 | Patient Model | Data model for patient needs to be created/adapted. | Model | Martin | Kevin |  |  |  |  | waiting
3.3 | 1 | Patient View | Create UI based on UI Prototype | UI | Philipp | Kevin |  |  |  |  | waiting
3.4 | 1 | Patient Controller | Implement functionality for patient view | Controller | Alain
3.5 | 1 | Patient View Test | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
4.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
4.2 | 1 | Appointment Model | Create Appointment Model | Model | Martin | Kevin |  |  |  |  | waiting
4.4 | 1 | Appointment implementation | Implement the functionality for an new Appointment | Controller | Alain | Kevin |  |  |  |  | waiting
4.5 | 1 | Appointment Tests | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
5.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
5.2 | 2 | Patient Model | Data model for patient needs to be created/adapted. | Model | Aline | Kevin |  |  |  |  | waiting
5.3 | 2 | Medication Model | Data model for medication needs to be created/adapted. | Model | Martin | Kevin |  |  |  |  | waiting
5.4 | 2 | Medication Prescription Controller | Implement functionality for medication prescription | Controller | Alain | Kevin |  |  |  |  | waiting
5.5 | 1 | Medication Prescription View | Create view and functionality for medication prescription | UI, Controller | Philipp | Kevin |  |  |  |  | waiting
5.6 | 1 | Medication Prescrition Test | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
6.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
6.2 | 2 | Medication Model | Data model for medication needs to be created/adapted. | Model | Martin | Kevin |  |  |  |  | waiting
6.3 | 2 | Medication Security Controller | Add functionality for Interaction, Contraindication, overdose usw. | Controller | Alain | Kevin |  |  |  |  | waiting
6.4 | 1 | Medication Security View | Create view and functionality for medication security | UI | Aline | Kevin |  |  |  |  | waiting
6.5 | 2 | Medication Security Tests | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
7.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
7.2 | 2 | Compendium Model | Data model for medication/compendium needs to be created/adapted. | Model/Repository | Aline | Kevin |  |  |  |  | waiting
7.3 | 2 | Compendium Controller | Implement functionality for compendium informations | Controller | Alain | Kevin |  |  |  |  | waiting
7.4 | 1 | Compendium View | Create view | UI | Philipp | Kevin |  |  |  |  | waiting
7.5 | 2 | Compendium Test | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
8.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
| 2 | Repository | Create needed DB Requests | Repository | Martin | Kevin
8.2 | 2 | Medication View Controller | Implement view functionalities | Controller | Lukas | Kevin |  |  |  |  | waiting
8.3 | 1 | Medication View | Create medication view and view functionality | UI | Philipp | Kevin |  |  |  |  | waiting
8.4 | 2 | Medication Test | Create view Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
9.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
9.2 | 2 | Medication Modification Controller | Adapt WS (WSDL, Endpoint) | Controller | Martin | Kevin |  |  |  |  | waiting
9.3 | 1 | Medication View | Adapt medication view and implement modification functionality | UI | Philipp | Kevin |  |  |  |  | waiting
9.4 | 2 | Medication Test | Create modification Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
10.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
10.2 | 2 | Medication Delete Controller | Implement medication delete functionality | Controller | Lukas | Kevin |  |  |  |  | waiting
10.3 | 1 | Medication View | Adapt medication view and implement delete functionality | UI | Philipp | Kevin |  |  |  |  | waiting
10.4 | 2 | Medication Test | Create delete Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
11.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
11.2 | 3 | Patient Model | Data model for patients needs to be created/adapted. | Model/Repository | Martin | Kevin |  |  |  |  | waiting
11.3 | 3 | Therapy Model | Data model for therapies needs to be created/adapted. | Model/Repository | Lukas | Kevin |  |  |  |  | waiting
11.4 | 3 | Therapy Prescription Controller | Create a test service for therapy based operations (WSDL, Endpoint) | Controller | Alain | Kevin |  |  |  |  | waiting
11.5 | 1 | Therapy Prescription View | Create view and functionality for therapy prescription | UI | Aline | Kevin |  |  |  |  | waiting
11.6 | 3 | Therapy Prescrition Test | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
12.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
12.2 | 3 | Therapy View Controller | Implement view functionality | Controller | Philipp | Kevin |  |  |  |  | waiting
12.3 | 1 | Therapy View | Create therapy view and view functionality | UI | Aline | Kevin |  |  |  |  | waiting
12.4 | 3 | Therapy Test | Create view Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
13.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
13.2 | 3 | Therapy Modification Controller | Implement therapy modification functionality | Controller | Alain | Kevin |  |  |  |  | waiting
13.3 | 1 | Therapy View | Adapt therapy view and implement modification functionality | UI | Aline | Kevin |  |  |  |  | waiting
13.4 | 3 | Therapy Test | Create modification Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
14.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
14.2 | 3 | Therapy Delete Controller | Implement therapy delete functionality | Controller | Alain | Kevin |  |  |  |  | waiting
14.3 | 1 | Therapy View | Adapt therapy view and implement delete functionality | UI | Aline | Kevin |  |  |  |  | waiting
14.4 | 3 | Therapy Test | Create delete Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
15.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
15.2 | 3 | SOAP View Controller | Implement functionality for SOAP View | Controller | Alain | Kevin |  |  |  |  | waiting
15.3 | 3 | SOAP Model | Data model for SOAP entries needs to be created/adapted. | Model | Lukas | Kevin |  |  |  |  | waiting
15.4 | 3 | Patient Model | Data model for patients needs to be created/adapted. | Model | Martin | Kevin |  |  |  |  | waiting
15.5 | 1 | SOAP View | Create SOAP List view and implement view functionalities | UI | Aline | Kevin |  |  |  |  | waiting
15.6 | 3 | SOAP View Test | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
16.1 | 1 | Database | Create tables | Database | Lukas | Kevin |  | 0.5 |  |  | waiting
16.2 | 3 | Create SOAP Entry Controller | Implement create functionality for SOAP Entries | Controller | Alain | Kevin |  |  |  |  | waiting
16.3 | 1 | Create SOAP Entry View | Create a view to create SOAP entries | UI | Aline | Kevin |  |  |  |  | waiting
16.4 | 3 | Create SOAP Entry Test | Create Testcases | Test | Kevin | Kevin |  |  |  |  | waiting
7.5

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180